## Sheet1
Risk assessment with Matrix |  |  |  |  | key: Higher the number higher the severity
Impact
|  |  | Non-existent | Slight disruptive | Moderate | Highly disruptive | Severly disrupted
| Chance | significant probability | 5 | 10 | 15 | 20 | 25
|  | higher probability | 4 | 9 | 14 | 19 | 24
|  | 50/50 probability | 3 | 8 | 13 | 18 | 23
|  | low probability | 2 | 7 | 12 | 17 | 22
|  | lowest probability | 1 | 6 | 11 | 16 | 21
| Risk Description | Statement | Response | Severity
| Loss of hardware | Loss of any Hardware including the laptop itself or CPU | You would have to purchase a new laptop and hope you have not lost any critical data | 21
| loss of software | loss of software including any critical infastructure you depend on due to hack attacks etc | You would have to find a new software which could result in losing critical data | 22
| Human error | Human errors could cause codebase to break or for critical data to be deleted or misplaced | You would have to redo any lost work and spend time trying to find any mistakes if you break codebase due to error | 15
| Internet/wifi issues | Internet network could fail or internet hardware could fail. If key changes need to be submitted this could be very disruptive | You would have to diagnose any faults or contact the internet provider | 12
| Human disease | At this time there is a highly spreadable virus that can impair mental functions to a lower standard than if you are well | I have had covid through this course and started to feel better at the start of the project. This did affect my ability to concentrate for longer periods of time | 20
| Not understanding the project brief | If you do not understand the brief you could end up not getting the MVP | This could be highly disruptive and waste alot of time trying to comprehend the the brief | 18